ACTION PLAN 2024-2025

ABC University - Faculty of Engineering & Technology

Year 1 Implementation of Strategic Plan 2024-2028

================================================================================

INTRODUCTION

This Action Plan for 2024-2025 operationalizes Year 1 of the Faculty's Strategic Plan 2024-2028. It translates strategic objectives into concrete actions, assigns responsibilities, allocates resources, and establishes timelines for achievement.

The action plan focuses on quick wins and foundational initiatives that will create momentum for long-term strategic success. Priority areas for Year 1 include: launching the Career Development Center, initiating curriculum redesign processes, establishing research centers, deploying the new LMS, and securing initial industry partnerships.

Each action item is linked to specific strategic objectives, ensuring direct alignment between operational activities and strategic goals. Progress will be monitored monthly through departmental reports and quarterly reviews by the Strategic Implementation Committee.

PILLAR 1 ACTIONS: ACADEMIC EXCELLENCE & CURRICULUM INNOVATION

Action A1.1: Establish Curriculum Innovation Task Force

Linked to: SO1.1
Description: Form a 12-member task force including faculty, industry experts, and students to lead curriculum redesign. Conduct needs assessment and benchmarking against top 20 global engineering programs.
Timeline: February 2024 - May 2024
Responsible: Associate Dean (Academic)
Resources: $50,000 for consultancy and research
Deliverables: Curriculum framework document, benchmark report, stakeholder consultation summary
Milestones:

- Task force formation (February)

- Needs assessment completion (April)

- Framework approval (May)

Action A1.2: Pilot Project-Based Learning in 4 Core Courses

Linked to: SO1.1, SO1.3
Description: Redesign 4 undergraduate courses (Engineering Design, Data Structures, Thermodynamics, Circuit Analysis) to incorporate industry-based projects, team collaboration, and authentic assessment.
Timeline: June 2024 - December 2024
Responsible: Department Heads
Resources: $80,000 for course development, industry partner coordination
Deliverables: 4 redesigned course syllabi, project partner agreements, assessment rubrics
Milestones:

- Course selection (June)

- Partner identification (August)

- Pilot launch (September)

- Evaluation (December)

Action A1.3: Initiate ABET Accreditation Process

Linked to: SO1.2
Description: Engage accreditation consultants, conduct gap analysis, and prepare self-study documentation for Computer Science and Electrical Engineering programs.
Timeline: April 2024 - March 2025
Responsible: Accreditation Coordinator
Resources: $120,000 for consultancy, documentation, site visit preparation
Deliverables: Gap analysis report, self-study documents, evidence repository
Milestones:

- Consultant engagement (April)

- Gap analysis (July)

- Self-study draft (December)

- Final submission (March 2025)

Action A1.4: Develop AI & Machine Learning Specialization

Linked to: SO1.3
Description: Design new Master's program in AI & ML including curriculum, lab requirements, faculty recruitment plan, and industry advisory board formation.
Timeline: March 2024 - December 2024
Responsible: CS Department Head
Resources: $150,000 for curriculum development, lab setup, marketing
Deliverables: Program proposal, accreditation application, recruitment plan, marketing materials
Milestones:

- Curriculum design (March-June)

- University approval (August)

- Accreditation submission (October)

- Student recruitment launch (December)

Action A1.5: Faculty Development Scholarship Program

Linked to: SO1.4
Description: Launch scholarship program supporting 10 faculty members to pursue doctoral studies at partner universities, with teaching load adjustments and financial support.
Timeline: January 2024 - Ongoing
Responsible: HR & Faculty Development Office
Resources: $400,000 annually for scholarships and replacement teaching
Deliverables: Scholarship guidelines, selection criteria, partnership agreements with universities
Milestones:

- Program announcement (January)

- Application deadline (March)

- Scholar selection (May)

- Enrollment support (August)

PILLAR 2 ACTIONS: STUDENT SUCCESS & EMPLOYABILITY

Action A2.1: Establish Career Development Center

Linked to: SO2.1
Description: Set up dedicated Career Development Center with 5 staff members (Director, 2 Career Counselors, Industry Liaison Officer, Administrative Assistant), office space, and systems infrastructure.
Timeline: January 2024 - May 2024
Responsible: Dean's Office
Resources: $250,000 for setup, staffing, and first-year operations
Deliverables: Operational Career Center, staff appointments, service catalog, online platform
Milestones:

- Space allocation (January)

- Staff recruitment (February-March)

- Systems deployment (April)

- Official launch (May)

Action A2.2: Internship Partnership Development

Linked to: SO2.2
Description: Secure internship placement agreements with 25 companies across technology, manufacturing, and consulting sectors. Target 400 internship positions for current students.
Timeline: February 2024 - December 2024
Responsible: Career Development Center Director
Resources: $60,000 for partnerships, student placement coordination
Deliverables: 25 signed MoUs, internship database, placement tracking system
Milestones:

- Company outreach (February-April)

- Agreement finalization (May-July)

- Student matching (August-September)

- Placements (October-December)

Action A2.3: Launch Professional Skills Development Program

Linked to: SO2.3
Description: Implement mandatory professional development workshops for all undergraduates covering: technical communication, leadership, teamwork, presentation skills, and professional ethics. Minimum 40 hours per student.
Timeline: June 2024 - Ongoing
Responsible: Student Affairs Office
Resources: $90,000 for facilitators, materials, certification
Deliverables: Workshop curriculum, facilitator training, attendance tracking system, competency certificates
Milestones:

- Program design (June)

- Facilitator recruitment (July)

- Pilot workshops (August)

- Full rollout (September)

Action A2.4: Alumni Mentorship Program Launch

Linked to: SO2.4
Description: Create structured mentorship program connecting 200 students with alumni mentors. Develop matching algorithm, orientation materials, and tracking mechanisms.
Timeline: March 2024 - December 2024
Responsible: Alumni Relations Office
Resources: $45,000 for platform development, events, recognition
Deliverables: Mentorship platform, 200 active mentor-mentee pairs, program guidelines, evaluation framework
Milestones:

- Mentor recruitment (March-May)

- Platform launch (June)

- Matching completion (August)

- Mid-year review (December)

Action A2.5: Academic Early Warning System Implementation

Linked to: SO2.5
Description: Deploy predictive analytics system tracking student performance indicators (attendance, grades, engagement). Provide targeted interventions including tutoring, counseling, and academic coaching.
Timeline: May 2024 - December 2024
Responsible: Academic Affairs Office
Resources: $80,000 for software licensing, training, support services
Deliverables: Analytics dashboard, intervention protocols, student support team, weekly reports
Milestones:

- System procurement (May)

- Staff training (July)

- Pilot implementation (August)

- Full deployment (September)

PILLAR 3 ACTIONS: RESEARCH EXCELLENCE & INNOVATION

Action A3.1: Establish AI & ML Research Center

Linked to: SO3.2
Description: Create Center for AI & Machine Learning with dedicated space, high-performance computing infrastructure, and recruitment of 3 research faculty and 5 PhD students.
Timeline: March 2024 - December 2024
Responsible: Research Director
Resources: $600,000 for infrastructure, equipment, initial staffing
Deliverables: Operational research center, HPC cluster, 3 faculty appointments, 5 PhD enrollments
Milestones:

- Space renovation (March-May)

- Equipment procurement (June-August)

- Faculty recruitment (April-September)

- Center launch (October)

Action A3.2: Research Grant Application Support Program

Linked to: SO3.1, SO3.3
Description: Establish grant writing support office providing proposal development assistance, budget planning, and pre-submission review. Target 40 grant applications with $2M total requested funding.
Timeline: January 2024 - Ongoing
Responsible: Research Grants Officer
Resources: $100,000 for grant officer, workshops, editing services
Deliverables: 40 grant applications submitted, proposal development workshops, success rate tracking
Milestones:

- Office setup (January)

- Workshop series launch (February)

- Quarterly application targets (April, July, October)

- Year-end review (December)

Action A3.3: Postgraduate Recruitment Campaign

Linked to: SO3.4
Description: Launch targeted recruitment campaign for Master's and PhD programs including scholarships, international student outreach, and research showcase events. Target 50 new PhD and 100 new Master's enrollments.
Timeline: February 2024 - September 2024
Responsible: Postgraduate Admissions Office
Resources: $120,000 for marketing, scholarships, recruitment events
Deliverables: Marketing materials, virtual open days, scholarship offers, admission confirmations
Milestones:

- Campaign launch (February)

- International education fairs (March-May)

- Application deadline (June)

- Admission offers (July)

- Enrollment (September)

Action A3.4: Technology Transfer & IP Management Initiative

Linked to: SO3.5
Description: Establish Technology Transfer Office, develop IP policy, provide inventor training, and identify 10 commercializable research outputs for patent filing.
Timeline: April 2024 - March 2025
Responsible: Technology Transfer Officer
Resources: $150,000 for office setup, patent filing, legal consultation
Deliverables: IP policy document, 10 patent applications, commercialization assessments, inventor workshops
Milestones:

- Office establishment (April)

- Policy approval (June)

- Inventor training (July-August)

- Patent filings (October-March)

PILLAR 4 ACTIONS: DIGITAL TRANSFORMATION & INFRASTRUCTURE

Action A4.1: Learning Management System Deployment

Linked to: SO4.1
Description: Procure and implement enterprise LMS (Canvas/Moodle) with AI-powered analytics, mobile accessibility, and integration with existing student systems. Train 150 faculty members.
Timeline: January 2024 - August 2024
Responsible: IT Director & Educational Technology Team
Resources: $300,000 for licensing, customization, training, support
Deliverables: Fully operational LMS, 100% course migration, faculty training completion, student onboarding
Milestones:

- Vendor selection (January)

- System configuration (February-April)

- Faculty training (May-June)

- Course migration (July)

- Go-live (August)

Action A4.2: Laboratory Modernization Phase 1

Linked to: SO4.2
Description: Upgrade 6 priority laboratories (Electronics, Computer Networks, Manufacturing, Materials Testing, Renewable Energy, Robotics) with new equipment and virtual lab software.
Timeline: March 2024 - December 2024
Responsible: Facilities & Lab Manager
Resources: $800,000 for equipment, software licenses, installation
Deliverables: 6 modernized labs, equipment inventory, virtual lab platforms, safety protocols
Milestones:

- Needs assessment (March)

- Equipment procurement (April-June)

- Installation (July-October)

- Commissioning (November-December)

Action A4.3: Campus Network Upgrade

Linked to: SO4.3
Description: Deploy fiber optic backbone, upgrade WiFi to WiFi 6 standard, implement network security enhancements, and provide 1 Gbps connectivity to all academic buildings.
Timeline: February 2024 - October 2024
Responsible: IT Infrastructure Team
Resources: $500,000 for networking equipment, cabling, security systems
Deliverables: Upgraded network infrastructure, 100% WiFi coverage, security audit report
Milestones:

- Design completion (February)

- Equipment procurement (March-April)

- Installation (May-August)

- Testing & commissioning (September-October)

Action A4.4: Digital Administrative Systems Implementation

Linked to: SO4.4
Description: Implement integrated ERP system covering admissions, student records, examinations, HR, and finance. Migrate historical data and train 80 administrative staff.
Timeline: April 2024 - March 2025
Responsible: Systems Integration Manager
Resources: $450,000 for software, implementation, training, data migration
Deliverables: Operational ERP system, migrated data, trained staff, process documentation
Milestones:

- System selection (April)

- Configuration (May-August)

- Data migration (September-November)

- Staff training (December-January)

- Go-live (February 2025)

PILLAR 5 ACTIONS: INDUSTRY PARTNERSHIPS & COMMUNITY ENGAGEMENT

Action A5.1: Strategic Industry Partnership Development

Linked to: SO5.1
Description: Identify and establish formal partnerships with 8 target companies including: Microsoft, IBM, Siemens, Samsung, Huawei, Schneider Electric, ABB, and Cisco. Negotiate collaborative agreements covering internships, research, guest lectures, and equipment donations.
Timeline: January 2024 - December 2024
Responsible: Industry Relations Manager
Resources: $75,000 for relationship development, legal consultation, partnership events
Deliverables: 8 signed partnership agreements, collaboration frameworks, joint activity calendars
Milestones:

- Company prioritization (January)

- Initial meetings (February-April)

- Negotiation (May-August)

- Agreement signing (September-December)

Action A5.2: Industry Advisory Council Formation

Linked to: SO5.2
Description: Recruit 12 industry leaders representing diverse engineering sectors to form advisory council. Organize quarterly meetings and establish working groups for curriculum review and research priorities.
Timeline: February 2024 - Ongoing
Responsible: Dean's Office
Resources: $40,000 for meetings, member recognition, advisory activities
Deliverables: 12-member advisory council, meeting schedule, recommendation reports
Milestones:

- Member recruitment (February-April)

- Inaugural meeting (May)

- Q2 meeting (August)

- Q3 meeting (November)

Action A5.3: STEM Outreach Program Launch

Linked to: SO5.4
Description: Develop and deliver hands-on STEM workshops for secondary school students covering robotics, coding, renewable energy, and engineering design. Target 2,500 students in Year 1 through 50 workshop sessions.
Timeline: May 2024 - Ongoing
Responsible: Community Engagement Coordinator
Resources: $85,000 for materials, transportation, student facilitators, marketing
Deliverables: Workshop curriculum, school partnerships, 50 completed sessions, impact evaluation
Milestones:

- Program development (May)

- School partnerships (June)

- Workshop series begins (July)

- Quarterly evaluations (October, January)

Action A5.4: Alumni Engagement Platform & Database

Linked to: SO5.5
Description: Develop comprehensive alumni database, launch online engagement platform, organize alumni reunion events, and establish alumni chapters in 3 major cities.
Timeline: March 2024 - December 2024
Responsible: Alumni Relations Director
Resources: $95,000 for platform development, database creation, events
Deliverables: Alumni database (5,000+ records), engagement platform, 3 city chapters, annual reunion event
Milestones:

- Database development (March-May)

- Platform launch (June)

- Chapter formation (August-October)

- Reunion event (November)

RESOURCE SUMMARY & BUDGET ALLOCATION

Total Year 1 Budget: $5,165,000

Budget Breakdown by Strategic Pillar:

- Pillar 1 (Academic Excellence): $800,000 (15.5%)

- Pillar 2 (Student Success): $525,000 (10.2%)

- Pillar 3 (Research Excellence): $970,000 (18.8%)

- Pillar 4 (Digital Transformation): $2,050,000 (39.7%)

- Pillar 5 (Industry Partnerships): $295,000 (5.7%)

- Contingency & Administration: $525,000 (10.1%)

Funding Sources:

- University allocation: $3,500,000 (67.8%)

- Industry partnerships & grants: $1,000,000 (19.4%)

- Tuition revenue increase: $400,000 (7.7%)

- Alumni donations: $265,000 (5.1%)

MONITORING & EVALUATION FRAMEWORK

Monthly Reviews

Department heads submit progress reports on assigned action items, including milestones achieved, challenges encountered, and budget utilization.

Quarterly Strategic Reviews

Strategic Implementation Committee conducts comprehensive reviews assessing:

- Action completion rates

- KPI progress

- Budget variance analysis

- Risk assessment updates

- Stakeholder feedback summary

Annual Comprehensive Evaluation

End-of-year evaluation measuring:

- Strategic objective achievement (percentage completion)

- ROI analysis for major investments

- Stakeholder satisfaction surveys

- Comparative benchmarking against peer institutions

- Recommendations for Year 2 action plan adjustments

Performance Dashboard

Real-time dashboard tracking 50+ metrics including enrollment numbers, research outputs, partnership activities, financial performance, and student outcomes. Accessible to senior leadership and department heads.

RISK MANAGEMENT

Identified Risks and Mitigation Strategies

Risk 1: Budget Constraints

- Mitigation: Phased implementation, prioritization matrix, alternative funding sources

Risk 2: Faculty Recruitment Challenges

- Mitigation: Competitive compensation packages, flexible work arrangements, early recruitment campaigns

Risk 3: Technology Implementation Delays

- Mitigation: Experienced vendors, pilot testing, change management support

Risk 4: Low Student Engagement

- Mitigation: Communication campaigns, incentive programs, feedback mechanisms

Risk 5: Industry Partnership Development

- Mitigation: Value proposition development, alumni network leverage, multi-tier partnership models

CONCLUSION

This Action Plan 2024-2025 provides a concrete roadmap for the first year of our strategic journey. Through disciplined execution, collaborative effort, and continuous monitoring, we will establish strong foundations for long-term success.

Each action has been carefully designed to create tangible value while building momentum toward our 2028 strategic goals. Success requires commitment from all stakeholders, and we are confident that our collective dedication will drive transformative change.

Regular reviews and adaptive management will ensure we remain responsive to emerging opportunities and challenges, maintaining our trajectory toward becoming a globally recognized center of excellence in engineering education.

Document Version: 1.0
Approval Date: January 2024
Reporting Cycle: Monthly (Departmental), Quarterly (Strategic Committee)
Review Date: December 2024